## Sheet1
Product Backlog
Id | Story | Priorty(5 = Highest) | Time Estimate(hours) | Time Took(hours) | Status | Priorty
001.1-OzuMopolitan | Introduction | 5 | 1.5 | 1.4 | Complete | 1 - Low
001.2-OzuMopolitan | Server Side of the Project | 5 | 5 | 5.4 | Complete | 5 - High
001.3-OzuMopolitan | Client Side of the Project | 5 | 3 | 3 | Complete
001.4-OzuMopolitan | Documentation | 5 | 2 | 2 | Complete
002.1-OzuMopolitan | Meeting with the customer | 5 | 1 | - | Incomplete
002.2-OzuMopolitan | Server Side of the Project (2nd Sprint) | 5 | 4.5 | - | Incomplete
002.3-OzuMopolitan | Client Side of the Project (2nd Sprint) | 5 | 4.5 | - | Incomplete
002.4-OzuMopolitan | Documentation (2nd Sprint) | 5 | 2 | - | Incomplete
Sprint Backlog
Id | Story | Responsible Person | Time Estimate(hours) | Time Took(hours) | Status
001.1.0 | Introduction |  |  |  | Week 1 Done
001.1.1 | Meeting with the group members and customer | All | 0.3 | 0.2 | Complete
001.1.2 | Project ideas and finalize the decision | All | 0.4 | 0.5 | Complete
001.1.3 | Brainstorming about the UI | All | 0.5 | 0.5 | Complete
001.1.4 | Assigning duties | All | 0.3 | 0.2 | Complete
001.2.0 | Server Side of the Project |  |  |  | Week 1 Done
001.2.1 | Methods for "Room" (openRoom, postInRoom, browseRoom) | Ahmad Soltani | 1 | 0.8 | Complete
001.2.2 | Methods for "Post" (editPost, postInRoom, browsePost) | Ahmad Soltani | 0.7 | 0.8 | Complete
001.2.3 | Methods for "Comment" (commentOnPost, commentOnComment, editComment) | Ahmad Soltani | 0.7 | 0.8 | Complete
001.2.4 | Building a simple php server for communication with sql server | Uğurcan Tunçdöken | 1 | 1 | Complete
001.2.5 | Adding methods on php(createUser, createPost, createRoom) | Uğurcan Tunçdöken | 1 | 1 | Complete
001.2.6 | Basic adaptation between servers | Uğurcan Tunçdöken & Ahmad Soltani | 0.6 | 1 | Complete
001.3.0 | Client Side of the Project |  |  |  | Week 1 Done
001.3.1 | Created simple UI (only visual) | Amin Dorostian & Deniz Ankay | 1 | 1 | Complete
001.3.2 | Created sideBar (using google material design) | Amin Dorostian & Deniz Ankay | 1 | 1 | Complete
001.3.3 | Room design | Amin Dorostian & Deniz Ankay | 0.5 | 0.5 | Complete
001.3.4 | Post page design | Amin Dorostian & Deniz Ankay | 0.5 | 0.5 | Complete
001.4.0 | Documentation |  |  |  | Week 1 Done
001.4.1 | Introduced project tools and diagram | Athar Khodabakhsh | 1 | 1 | Complete
001.4.2 | Sprint Backlog | Fırat Kaptan | 1 | 1 | Complete
002.1.0 | Meeting with the customer |  |  |  | Week 2
002.1.1 | Demo | All | 0.5 |  | Incomplete
002.1.2 | Discussing the demo with the customer | All | 0.5 |  | Incomplete
002.2.0 | Server Side of the Project (2nd Sprint) |  |  |  | Week 2
002.2.1 | Vote methods (votePost, voteComment, editVote) | Ahmad Soltani & Fırat Kaptan | 1.5 |  | Incomplete
002.2.2 | Follow methods (followUser, followRoom, unfollow) | Ahmad Soltani & Fırat Kaptan | 1.5 |  | Incomplete
002.2.3 | Adding new methods on php server according to this changes | Ahmad Soltani & Fırat Kaptan | 1.5 |  | Incomplete
002.3.0 | Client Side of the Project (2nd Sprint) |  |  |  | Week 2
002.3.1 | Establishing the connection with server | Amin Dorostian & Uğurcan Tunçdöken | 1.5 |  | Incomplete
002.3.2 | Fetching data from server | Amin Dorostian & Uğurcan Tunçdöken | 1.5 |  | Incomplete
002.3.3 | Improving design | Amin Dorostian & Uğurcan Tunçdöken | 1.5 |  | Incomplete
002.4.0 | Documentation (2nd Sprint) |  |  |  | Week 2
002.4.1 | Meeting with the group members at the end of the sprint | Athar Khodabakhsh & Deniz Ankay | 1 |  | Incomplete
002.4.2 | Sprint Backlog | Athar Khodabakhsh & Deniz Ankay | 1 |  | Incomplete